## Projects Overview
| planner biocodegaming |  |  |  |  | groen = dag voorbij geel = vrij/weekend
day | date | Project |  | Progress | End | Notes
Di | 2017-05-16 | functioneel en technische ontwerp af maken. | 0.01% |  | 0 | documentatie aanpassen als nodig is
WO | 2017-05-17 | damian is begonnen met coderen. Alex werkt documenten af. | 0.01% |  | 0 | we werken langer aan het ontwerp vandaag
DO | 2017-05-18 | niet aan PT gewerkt | 0.01% |  | 0 | werken nog steeds aan documenten
VR | 2017-05-19 | nog steeds met documenten bezig door verwarring en aanpassingen | 0.01% |  | 0 | het uurt te lang ugh
ZO | 2017-05-20 | weekend | 0.01% |  | 0
ZO | 2017-05-21 | weekend | 0.01% |  | 0
MA | 2017-05-22 | geen PT | 0.01% |  | 0 | we hebben tijdens SLB aan documenten gewerkt
DI | 2017-05-23 | documenten samen voor het laatst afronden | 0.01% |  | 0 | alex finished de documenten
WO | 2017-05-24 | damian is begonnen met het register system, alex aan het forum | 0.01% |  | 0 | login bugged, moet nocker voor hulp vragen
DO | 2017-05-25 | hemelvaart | 0.01% |  | 0
VR | 2017-05-26 | vrij | 0.01% |  | 0
ZA | 2017-05-27 | weekend | 0.01% |  | 0
ZO | 2017-05-28 | weekend | 0.01% |  | 0
MA | 2017-05-29 | geen PT | 0.01% |  | 0
DI | 2017-05-30 | alex heeft een basic forum en damian is met de login en reg bezig | 0.01% |  | 0 | forum wordt ge implementeerd
WO | 2017-05-31 | alex werkt verder met de forum en damian werkt enkele musts af | 0.01% |  | 0
DO | 2017-06-01 |  | 0.01% |  | 0
VR | 2017-06-02 | alex heeft logout gefinished | 0.01% |  | 0 | damian was ziek
ZA | 2017-06-03 | weekend | 0.01% |  | 0
ZO | 2017-06-04 | weekend | 0.01% |  | 0
MA | 2017-06-05 | weekend | 0.01% |  | 0
DI | 2017-06-06 | alex leert een pm system te maken en damian heeft user info page af | 0.01% |  | 0
WO | 2017-06-07 | alex is bezig met inventory en damian werkt aan posters | 0.01% |  | 0
DO | 2017-06-08 | geen PT | 0.01% |  | 0
VR | 2017-06-09 | poster begin en indeling voor filmpje | 0.01% |  | 0
ZA | 2017-06-10 |  | 0.01% |  | 0
ZO | 2017-06-11 | weekend | 0.01% |  | 0
MA | 2017-06-12 | damian heeft poster's gemaakt en alex maakt de app | 0.01% |  | 0
DI | 2017-06-13 | damian heeft adjustments gemaakt aan de posters en alex werkt aan de app | 0.01% |  | 0
WO | 2017-06-14 | alex werkt og aan de app en damian maakt user inventory | 0.01% |  | 0
DO | 2017-06-15 | alex werkt og aan de app en damian maakt user inventory | 0.01% |  | 0
VR | 2017-06-16 |  | 0.01% |  | 0
ZA | 2017-06-17 | weekend | 0.01% |  | 0
ZO | 2017-06-18 | weekend | 0.01% |  | 0
MA | 2017-06-19 |  | 0.01% |  | 0
DI | 2017-06-20 |  | 0.01% |  | 0
WO | 2017-06-21 |  | 0.01% |  | 0
DO | 2017-06-22 |  | 0.01% |  | 0
VR | 2017-06-23 |  | 0.01% |  | 0
ZA | 2017-06-24 |  | 0.01% |  | 0
Formulas:
End = MAX(IF((Tasks[Project]=Projects[[#This Row],[Project]])*(Tasks[Start]>0),Tasks[[Start]:[End]]))

## Task Details (hidden)
Task Details
Start | End | Project | Task | Done | Notes
2011-10-01 | 2011-10-15 | Plan Vacation | Choose between tropical & temperate | 1 | Chose tropical. Belize here we come!
2011-10-15 | 2011-12-31 | Plan Vacation | Monitor spring air fare rates online | 1
2011-10-15 |  | Plan Vacation | Study the history and culture of Belize
2011-10-15 | 2011-10-20 | Plan Vacation | Study resort reviews | 1
2011-10-20 |  | Plan Vacation | Make reservations at resort | 1 | April 19 through April 30
2011-10-20 | 2011-11-15 | Plan Vacation | Get passports for the entire family |  | Consider the rush option…
2011-09-01 | 2011-09-30 | Train for Marathon | 10 miles a day | 1 | Race is on April 18
2011-10-01 | 2011-10-31 | Train for Marathon | 12 miles a day | 1
2011-11-01 | 2011-11-30 | Train for Marathon | 14 miles a day
2011-12-01 | 2012-04-15 | Train for Marathon | 15 miles a day
2012-04-16 |  | Train for Marathon | Travel to marathon
2012-04-16 | 2012-04-17 | Train for Marathon | Inspect course |  | 10 mile jogs each day
2012-04-18 |  | Train for Marathon | Cross the finish line under 3 hours! |  | Now go to Belize!
2011-09-10 |  | Plan Sara's Surprise Party | Send party invitations | 1 | Surprise birthday party on October 3
2011-09-20 |  | Plan Sara's Surprise Party | Order catering | 1
2011-09-22 |  | Plan Sara's Surprise Party | Secure the entertainment | 1
2011-10-03 |  | Plan Sara's Surprise Party | Party day! | 1 | It was awesome. She had no idea!
2011-10-01 | 2011-10-15 | Enroll Sara in Swimming Lessons | Compare local area community center prices
Projects Overview
TIP: Double-click in Done column when task is complete.